## PRODUCTION SCHEDULE
[10 empty] | EBV to K |  |  | C4 | C4 UBOOT |  |  | C4 | [6 empty] | C4 |  |  | 1GB |  | MOVE | [12 empty] | 2.0 | [5 empty] | 2.0
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64
|  |  |  | 2009-10-09 | 2009-10-16 | 2009-10-23 | 2009-10-30 | 2009-11-06 | 2009-11-13 | 2009-11-20 | 2009-11-27 | 2009-12-04 | 2009-12-11 | 2009-12-18 | 2009-12-25 | 2009-01-01 | 2009-01-08 | 2010-01-15 | 2010-01-22 | 2010-01-29 | 2010-02-05 | 2010-02-12 | 2010-02-19 | 2010-02-26 | 2010-03-05 | 2010-03-12 | 2010-03-19 | 2010-03-26 | 2010-04-02 | 2010-04-09 | 2009-04-16 | 2009-04-23 | 2009-04-30 | 2009-05-07 | 2009-05-14 | 2009-05-21 | 2009-05-28 | 2009-06-04 | 2009-06-11 | 2009-06-18 | 2009-06-25 | 2009-07-02 | 2009-07-09 | 2009-07-16 | 2009-07-23 | 2010-07-30 | 2010-08-08 | 2010-08-14 | 2010-08-20 | 2010-08-27 | 2010-09-03 | 2010-09-10 | 2010-09-17 | 2010-09-24 | 2010-10-01 | 2010-10-08 | 2010-10-15 | 2010-10-22 | 2010-10-29 | 2010-11-05 | 2010-11-12 | 2010-11-19 | 2010-11-26 | 2010-12-03 | 2010-12-10 | 2010-12-17 | 2010-12-25
REV C3 | Beagle C3F Prod #1 (160) |  |  | 1: 0; 3: MEM/OMAP 2K; 4: ASSY; 5: TEST; 6: 0
| Beagle C3F Prod #2 (300) |  |  | 1: 0; 3: MEM/OMAP 2K; 4: 0; 5: ASSY; 6: ASSY; EBV to K 7: TEST
| SparkFun Shipments |  |  | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
| IDA Shipments C3F |  |  | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
| DK Production C3F (700) |  |  | 100 | 100 | 0 | 150 | 0 | 150 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700
| TOTAL C3F Production |  |  | 100 | 400 | 0 | 150 | 0 | 150 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
REV C4 Production | Beagle C4 Prod #1 (2000) |  |  | C4 UBOOT 11: ASSY (2000)1900; C4 UBOOT 13: TEST; C4 14: TEST; C4 15: TEST; C4 16: TEST; C4 17: TEST; C4 18: TEST; C4 19: 1850
| Beagle C4 Prod #2 (1300) |  |  | 3: MEM/OMAP 2K; C4 UBOOT 11: PCB (1500); C4 14: COMPONENTS; C4 19: ASSY; C4 21: TEST; C4 22: TEST; C4 23: TEST; 1GB 24: TEST; 1GB 25: 1300
| Beagle C4 Prod #3(700) |  |  | 1GB 24: PARTS; 1GB 25: ASSY; MOVE 27: Test; MOVE 28: Test; MOVE 29: 675
| Beagle C4 Prod #4 (700) |  |  | MOVE 26: PARTS; MOVE 27: ASSY; MOVE 29: Test; MOVE 30: Test; MOVE 31: 675
| Beagle C4 Prod #5 (700) |  |  | MOVE 28: PARTS; MOVE 29: ASSY; MOVE 31: Test; MOVE 32: Test; MOVE 33: 675
| Beagle C4 Prod #6 (700) |  |  | MOVE 30: PARTS; MOVE 31: ASSY; MOVE 33: Test; MOVE 34: Test; MOVE 35: 675
| Beagle C4 Prod #7 (700) |  |  | MOVE 33: PARTS; MOVE 34: ASSY; MOVE 36: Test; MOVE 37: Test; MOVE 38: 675
| Beagle C4 Prod #8 (700) |  |  | MOVE 35: PARTS; MOVE 36: ASSY; MOVE 38: Test; 2.0 39: Test; 2.0 40: Test; 2.0 41: 675
| Beagle C4 Prod #9 (500)***** |  |  | MOVE 38: PARTS; 2.0 39: ASSY; 2.0 41: Test; 2.0 42: Test; 2.0 43: Test; 2.0 44: 325
| EBV (400) C4 | 425 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DK #1 C4 (2000) | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 250 | 275 | 275 | 0 | 0 | 200 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DK #2 C4 (2350) | 2350 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 0 | 200 | 200 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Spark Production #1 C4 (250) | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Spark Production #2 C4 (500) | 500 | 75 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 50 | 25 | 50 | 50 | 25 | 25 | 0 | 25 | 25 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mouser #1 C4 (500) | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 50 | 0 | 0 | 100 | 0 | 100 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mouser #2 C4 (500) | 500 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 50 | 50 | 25 | 50 | 50 | 50 | 0 | 25 | 25 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mouser #3 C4 (500) | 500 | 0 | MOVE 28: 0; MOVE 29: 0; MOVE 30: 0; MOVE 31: 0; MOVE 32: 0; MOVE 33: 0; MOVE 34: 0; MOVE 35: 0; MOVE 36: 0; MOVE 37: 0; MOVE 38: 0; 2.0 39: 100; 2.0 40: 75; 2.0 41: 150; 2.0 42: 175; 2.0 43: 0; 2.0 44: 0; 2.0 45: 0; 2.0 46: 0; 2.0 47: 0; 2.0 48: 0; 2.0 49: 0; 2.0 50: 0; 2.0 51: 0; 2.0 52: 0
| IDA Production #2 C4 (250) | 50 | 50 | C4 23: 0; 1GB 24: 50; 1GB 25: 0; MOVE 26: 0; MOVE 27: 0; MOVE 28: 0; MOVE 29: 0; MOVE 30: 0; MOVE 31: 0; MOVE 32: 0; MOVE 33: 0; MOVE 34: 0; MOVE 35: 0; MOVE 36: 0; MOVE 37: 0; MOVE 38: 0; 2.0 39: 0; 2.0 40: 0; 2.0 41: 0
| Farnell #1 C4 (250) | 250 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wattertot #1 C4 (250) | 250 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Special Comp C4 #1 (125) | 125 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Special Comp C4 #2 (250) | 250 | 0 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 75 | 25 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total C4 PRODUCTION | 7950 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 250 | 275 | 375 | 0 | 0 | 350 | 300 | 300 | 350 | 0 | 0 | 275 | 400 | 350 | 325 | 325 | 350 | 325 | 350 | 0 | 375 | 300 | 500 | 100 | 75 | 150 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 75 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-xM PRODUCTION | -xM Software | bar: MOVE 29 to MOVE 32
| BeagleXM Rev A Pre-Prod #1 25 |  |  | C4 22: PCB (5 WKS); 1GB 25: PARTS; MOVE 26: MICRON; MOVE 28: PCBS (1100); MOVE 30: ASSY; MOVE 31: TEST; MOVE 32: 25
| BeagleXM Rev A Prod #1 325 |  |  | EBV to K 7: Long Lead Items (5000, scheduled as 1K, 1K, 1K,……..1K)); C4 23: PCBS; 1GB 25: PARTS; MOVE 26: MICRON; MOVE 31: ASSY; MOVE 33: Test; MOVE 34: Test; MOVE 35: 325
| BeagleXM Rev A Prod #2 700 |  |  | MOVE 37: ASSY; 2.0 39: Test; 2.0 40: Test; 2.0 41: Test; 2.0 42: 650
| BeagleXM Rev A Prod #3 700 |  |  | MOVE 33: PCB (1400_; 2.0 40: ASSY; 2.0 42: Test; 2.0 43: Test; 2.0 44: 675
| BeagleXM Rev A Prod #4 700 |  |  | 2.0 42: ASSY; 2.0 44: Test; 2.0 45: Test; 2.0 46: 675
| BeagleXM Rev B Prod #1 1000 |  |  | 2.0 44: ASSY; 2.0 46: Test; 2.0 47: Test; 2.0 48: 975
| BeagleXM Rev B Prod #2 1550 | 5000 |  | 2.0 46: ASSY; 2.0 48: Test; 2.0 49: Test; 2.0 50: Test; 2.0 51: 1500
| BeagleXM Rev B Prod #3 1000 |  |  | 2.0 48: ASSY; 2.0 50: Test; 2.0 51: Test; 2.0 52: 525
| BeagleXM Rev B Prod #4 1000 |  |  | 2.0 50: ASSY; 2.0 52: Test; 2.0 53: Test; 2.0 54: 0
| BeagleXM Rev B Prod #5 1000 |  |  | 2.0 52: ASSY; 2.0 54: Test; 2.0 55: Test; 2.0 56: 0; 2.0 62: Test; 2.0 63: Test; 2.0 64: Test
| EBV (5) C4 Pretest |  |  | EBV to K 9: 5
| D/K RUNNING TOTAL |  |  | MOVE 29: 0; MOVE 30: 0; MOVE 34: 200; MOVE 35: 200; MOVE 36: 200; MOVE 37: 200; MOVE 38: 200; 2.0 39: 375; 2.0 40: 575; 2.0 41: 825; 2.0 42: 1125; 2.0 43: 1425; 2.0 44: 1725; 2.0 45: 2025; 2.0 46: 2475; 2.0 47: 2925; 2.0 48: 3375; 2.0 49: 3900; 2.0 50: 4425
| DK #1 XM A (5000) | 4425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 175 | 200 | 250 | 300 | 300 | 300 | 300 | 450 | 450 | 450 | 525 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Spark #1 XM A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mouser #1 XM A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| IDA #1 XM A (250) | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 75 | 0 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Farnell#1 XM A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wattertot #1 XM A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ESC | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Special Comp C4 #1 | 0 | 0 | bar: C4 UBOOT 11 to C4 UBOOT 13; MOVE 29 to 2.0 64
| TOTAL XM PRODUCTION | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 200 | 0 | 0 | 0 | 0 | 175 | 225 | 250 | 375 | 300 | 375 | 300 | 525 | 450 | 450 | 525 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL OUTPUT | 12750 | 4250 | [18 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 275 | 400 | 350 | 325 | 325 | 350 | 450 | 550 | 0 | 375 | 300 | 500 | 275 | 300 | 400 | 550 | 300 | 375 | 300 | 525 | 450 | 450 | 525 | 625 | 75 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| C4 Prod #3 Order Window |  |  | EBV to K 7: WINDOW #3; EBV to K 9: 14 Week Leadtime
| C4 Prod #4 Order Window |  |  | C4 14: WINDOW #4; C4 16: 14 week Lead Time
| C4 Prod #5 Order Window |  |  | C4 23: WINDOW #4; 1GB 25: 10 Week Leadtime
| C4 Prod #6 Order Window |  |  | MOVE 29: WINDOW #4; MOVE 31: 10 Week Leadtime
|  | PLANNED | SHIPPED | MOVE 35: XXXXX
[31 empty] | 2.0 SAMP |  | ESC 4/26-4/29 |  |  |  |  | ESC 6/4
| BeagleXM Development |  |  | 1: Layout (COMPL); 6: PCB FAB; C4 UBOOT 11: FAB; C4 17: LAYOUT FIX
| BeagleXM Proto 20 |  |  | C4 UBOOT 12: ASSY (25); C4 15: TEST; C4 19: Alpha Period
| BeagleXM Proto 20 |  |  | C4 18: ASSY (25); C4 20: Test; C4 21: Beta Period (SW)
| PART ORDER/REQ DATE |  |  | 6: ORDER; C4 22: 2009-03-05; MOVE 26: Micron 4G?; MOVE 28: 2009-04-16; MOVE 34: 2009-05-28; MOVE 35: ORDER; 2.0 39: 2009-07-02; 2.0 45: 2010-08-14; 2.0 51: 2010-09-24; 2.0 57: 2010-11-05
| 2.0 Prod #1 Order Window |  |  | C4 17: WINDOW #1; C4 19: 10 Week Leadtime
| 2.0 Prod #2 Order Window |  |  | C4 22: WINDOW #2; 1GB 24: 10 Week Leadtime
| 2.0 Prod #3 Order Window |  |  | MOVE 29: WINDOW #3; MOVE 31: 10 Week Leadtime
| 2.0 Prod #4 Order Window |  |  | MOVE 34: WINDOW #4; MOVE 36: 10 Week Leadtime
| 2.0 Prod #5 Order Window |  |  | 2.0 40: WINDOW #4; 2.0 42: 10 Week Leadtime
| 2.0 Prod #6 Order Window |  |  | 2.0 46: WINDOW #5; 2.0 48: 10 Week Leadtime
| 2.0 Prod #7 Order Window |  |  | 2.0 52: WINDOW #6; 2.0 54: 10 Week Leadtime
|  |  |  | 1: DISTR | STATUS | ORDERED | U/O
| EBV Stock |  |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| EBV Sold |  |  | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0
| EBV Ship |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 400 | #N/A
| DigiKey Stock |  |  | 128 | 145 | 0 | 0 | -50 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 700 | 775 | 850 | 650 | 450 | 450 | 550 | 400 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 300 | 400 | 500 | 750 | 1000 | 1250 | 1575 | 1900 | 1700 | 1500 | 1300 | 1100 | 900 | 700 | 500 | 300 | 100 | 300 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Digikey Sold |  |  | 250 | 114 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 564
| DigiKey Ship |  |  | 100 | 100 | 0 | 150 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 250 | 275 | 275 | 0 | 0 | 200 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 300 | 300 | 300 | 450 | 450 | 450 | 525 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 2600 | -3450
| Mouser Stock |  |  | 180 | 169 | 125 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 120 | 90 | 110 | 80 | 50 | 120 | 90 | 160 | 180 | 150 | 120 | 140 | 110 | 80 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mouser Sold |  |  | 21 | 11 | 44 | 94 | 31 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 201
| Mouser Ship |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 50 | 0 | 0 | 100 | 0 | 100 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500
| Spark Stock |  |  | 20 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 120 | 90 | 110 | 80 | 50 | 75 | 50 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Spark Sold |  |  | 20 | 20 | 44 | 6 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 90
| Spark Ship |  |  | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 300 | 250
| IDA Stock |  |  | 0 | 0 | 250 | 250 | 250 | 230 | 210 | 190 | 170 | 150 | 130 | 110 | 90 | 70 | 50 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 100 | 100 | 175 | 175 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
| IDA Sold |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| IDA Ship |  |  | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 75 | 0 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0
| Farnell Stock |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Farnell Sold |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0
| Farnell Ship |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250
| Brazil Stock |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 125 | 100 | 75 | 100 | 75 | 50 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Brazil Sold |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0
| Brazil Ship |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| XXX Stock |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 75 | 100 | 125 | 150 | 150 | 150 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275
| XXX Sold |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| XXX Ship |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 0 | -275
|  |  |  | 2: #N/A | #N/A
[25 empty] | DATE | QTY | D/K |  | Shipped |  | DATE | QTY
[18 empty] | Order Windows |  | Lead Time | Delivery Window |  |  |  | 2010-01-15 | 750 | 750 |  | 750
[18 empty] | C4 | [6 empty] | 2010-01-22 | 250 | 250 |  | 250
[18 empty] | 2009-11-16 | 2009-11-27 | 14 Weeks | 2009-03-19 | 2009-04-02 |  |  | 2010-01-29 | 275
[18 empty] | 2009-01-04 | 2009-01-15 | 14 Weeks | 2009-04-30 | 2009-05-14 |  |  | 2010-02-05 | 275
[18 empty] | 2009-03-12 | 2009-03-19 | 10 Weeks | 2009-06-04 | 2009-06-18 |  |  | 2010-02-26 | 200
[18 empty] | 2009-04-19 | 2009-04-30 | 10 Weeks | 2009-07-09 | 2009-07-23 |  |  | 2010-03-05 | 250
[18 empty] | 2 | [6 empty] | 2010-03-12 | 300
[18 empty] | 2009-01-25 | 2009-02-05 | 10 Weeks | 2009-04-09 | 2009-04-30
[18 empty] | 2009-03-01 | 2009-03-12 | 10 Weeks | 2009-05-21 | 2009-06-11
[18 empty] | 2009-04-19 | 2009-04-30 | 10 Weeks | 2009-07-02 | 2009-07-23 |  |  | 2010-03-19 | 350
[18 empty] | 2009-05-24 | 2009-06-04 | 10 Weeks | 2010-08-08 | 2010-08-27 |  |  | 2010-03-26 | 0
[18 empty] | 2010-08-16 | 2010-08-27 | 10 Weeks | 2010-09-17 | 2010-10-08 |  |  | 2010-04-02 | 0
[18 empty] | 2010-09-27 | 2010-10-08 | 10 Weeks | 2010-12-10 | 2010-12-25 |  |  | 2010-04-09 | 275
[25 empty] | TOTAL | 2925 | 1000 |  | 1000
Note on L74: Gerald Coley: Order 5K
Note on AB74: Gerald Coley: Receive 1K parts
Note on AH34: Gerald Coley: Waiting for wire transfer
Note on AH74: Gerald Coley: Receive 1K parts
Note on AN74: Gerald Coley: Receive 1K parts. Accelerate if needed.
Note on AO74: Gerald Coley: Order 2K parts if run rates are good.
Note on AS74: Gerald Coley: Receive 1K Parts. Acceelrate if needed.
Note on AY74: Gerald Coley: Receive 1K Parts. Acceelrate if needed.
Note on BE74: Gerald Coley: 1k of second buy. Acceelrate if needed.
Note on BK74: Gerald Coley: 1k of second buy. Acceelrate if needed.

## Sheet1
REPLACED OVERVOLTAGE CIRCUIT
1. Deleted U19, U31, and U32.
2. Deleted C214 and C212.
3. Added new U31 and U32, a NCP349MNAE overvoltage protection device.
ADDED DC POWER DETECTION
1. Moved Q2A to level shift nUSB_PWR.
2. Connected Q2A output to the TPS65950 GPIO as indication that the board is DC powered
when LOW.
CHANGED SD CONNECTOR DUE TO EOL OF CURRENT PART.
1. Replaced uSD connector with new part number.
2. Delete ,R144,R120,C211.
CHANGED PROCESSOR TO ES1.2

## xM_BOM_REVC
BEAGLE-xM PCB ASSEMBLY BOM
|  |  | REV | DESCRIPTION |  | DATE | BY
|  |  | A | Initial Release |  |  | GC
|  |  | A1 | Had R148 and R148 in the install and the DNI list at the same time. Changed to 4GB microSD card. |  | 2010-04-21 | GC
|  |  | A2 | Removed RP1 and added RP7. Replace L12 with a 0 ohm resistor. |  | 2010-04-26 | GC
Corrected several erros and added back in missing reference designators.
|  |  | A3 | Changed product revision number from A2 to A4. |  | 2010-09-14 | GC
Deleted Item #26 of the PCB assembly.
On Item #44 of the PCB Assembly deleted L12 and add R159.
On PCB Assembly iItem #1 changed PCB revision to Rev B.
Add R160, R155 and R156 to the DNI list.
On PCB Assembly Item #64, add R158 and increase quantity to 7.
On PCB Assembly Item #54, add R157 and increase quantity to 8.
On PCB Assembly Item #4 remove C212 and C214. Change quantity to 1.
On PCB Assembly Item #58 add R34. Change quantity to 10. Delete R34 from DNI list.
On PCB Assembly Item #6, remove C9. Add C9 to the DNI list. Reduce quantity to 118.
|  |  | B | Changed processor from ES1.0 to ES1.1 |  | 2010-10-26 | GC
|  |  | C | Changed processor from ES1.1 to ES1.2 |  | 2010-12-07 | GC
Replaced U31 and U32 with a NCP349MNAE, over voltage protection circuit. Removed all associated parts not used from orignal design.
On PCB Assembly item #31 replaced the uSD connector, with a SCHA5B0200 & changed PCB due to EOL of currently used connector.
On PCB changed footprint on C6 to match the part being purchased. No impact on BOM
Changed PCB revision to a Rev C. Changed top level revsion to a Rev C.
Changed resistor loading to enable SW to read a Rev C revision. Changed Item # R22 as a DNI and changed quantity from 5 to 4.
LEVEL |  |  | ITM | DESCRIPTION | REFERENCE DESIGNATORS | PART# | QTY
0 |  |  |  | Beagle -xM REV C
| 1 |  |  | Beagle -xM Box and Peripherals
|  | 2 | 1 | SD Card 4GB, Kingston w/adapter |  | 4G_MICROSD | 1
|  | 2 | 2 | BOX |  | BEAG_BOX | 1
|  | 2 | 3 | Label |  | LABEL_XM | 1
|  | 2 | 4 | Packing |  | BEAG+PACK | 1
|  | 2 | 5 | Standoff |  | SPACE_PLAS | 4
| 1 |  |  | Beagle XM PCB Assembly Rev B
|  | 2 | 1 | Beagle PCB 6 layer, 3.35"x3.25", Rev C |  | 500-5000-000 | 1
|  | 2 | 2 | BAT_LI_RTC | BT1 | VL-1220/VCN | 0
|  | 2 | 3 | CAP CER 10UF 6.3V X5R 0805 | C5,C111,C112,C118,C119,C128,C132,C136,C140,C144,C167,C189 | JMK212BJ106KD-T | 12
|  | 2 | 4 | CAP CER 10UF 25V Y5V 1206 | C6 | TMK316F106ZL-T | 1
|  | 2 | 5 | CAP TANT 100UF 6.3V 10% SMD | C160,C161,C162,C163 | B45196H1107M209V18 | 4
|  | 2 | 6 | CAP CER .10UF 10V X5R 0402 | C3,C7,C8,C12,C14,C15,C17,C19,C20,C24,C25,C26,C27,C28,C29,C30,C31,C32,C33,C34,C35,C36,C37,C38,C40,C41,C42,C43,C45,C46,C47,C48,C49,C50,C52,C53,C54,C56,C57,C58,C59,C60,C61,C62,C63,C64,C65,C66,C67,C68,C69,C70,C71,C72,C75,C76,C78,C83,C84,C85,C91,C98,C99,C104,C107,C110,C117,C138,C139,C143,C145,C146,C147,C148,C149,C150,C151,C152,C153,C154,C155,C156,C157,C158,C159,C164,C165,C168,C170,C171,C172,C173,C174,C175,C176,C180,C181,C182,C183,C185,C186,C191,C192,C193,C194,C195,C197,C204,C206 | LMK105BJ104KV-F | 110
|  | 2 | 7 | CAP CER 47PF 50V C0G 5% 0402 | C10,C11,C89,C90,C100,C101 | C1005C0G1H470J | 6
|  | 2 | 8 | CAP CERAMIC 4.7UF 6.3V X5R 0603 | C13,C16,C18,C21,C22,C23,C39,C44,C55,C77,C86,C105,C166,C169,C177,C184,C190,C205,C207 | ECJ-1VB0J475M | 19
|  | 2 | 9 | CAP CER 1UF 10V X5R 0402 | C73,C74,C79,C80,C81,C108,C109,C113,C114,C115,C116,C120,C121,C123,C124,C125,C126,C127,C129,C130,C131,C133,C134,C135,C137,C187,C196,C210,C213 | GRM155R61A105KE15D | 29
|  | 2 | 10 | CAP CERAMIC .001UF 16V X7R 0402 | C82 | CC0402KRX7R7BB102 | 1
|  | 2 | 11 | CAP CER 47UF 10V X5R 1210 | C87,C88 | GRM32ER61A476KE20L | 2
|  | 2 | 12 | CAP CERAMIC 100PF 25V NP0 0402 | C92,C93,C94,C95,C96,C97,C199 | C0402C101J3GACTU | 7
|  | 2 | 13 | CAP 22PF 50V CERAMIC 0402 SMD | C102,C103 | ECJ-0EC1H220J | 2
|  | 2 | 14 | CAP CER 2.2UF 6.3V X5R 0402 | C106,C122 | JMK105BJ225MV-F | 2
|  | 2 | 15 | CAP CER 22000PF 50V X7R 0402 | C198 | GRM155R71H223KA12D | 1
|  | 2 | 16 | CAP CERAMIC 33PF 50V NP0 0402 | C178,C179 | C0402C330J5GACTU | 2
|  | 2 | 17 | PulseGuard Supressors 0603 24VDC 45A | D1,D2,D3,D4,D8,D9,D10,D11 | PGB1010603MR | 8
|  | 2 | 18 | LED GREEN CLEAR 0603 SMD | D5,D6,D7,D12,D14 | LTST-C190GKT | 5
|  | 2 | 19 | LED RED CLEAR 0603 SMD | D13 | LTST-C190CKT | 1
|  | 2 | 20 | HDR2_.1x.1 | J2 | 67997-472HLF | 0.055556
|  | 2 | 21 | INDUCTOR 3.3UH 10% 0603 SMD | L2,L3 | 83R3K-T | 2
|  | 2 | 22 | IND,POWER,1.0UH,30%,ISAT=2.0A,SMT | L4,L6 | LPS3015-102MLC | 2
|  | 2 | 23 | IND,POWER,1.0UH,30%,SMT | L5 | LPS3010-102MLC | 1
|  | 2 | 24 | FERRITE CHIP 300 OHM 500MA 0603 | L7,L8,L9 | MMZ1608R301A | 3
|  | 2 | 25 | FERRITE CHIP 120 OHM 2000MA 0603 | L10,L11 | BLM18PG121SN1D | 2
|  | 2 | 26 | CONN RECEPT USB 5POS RT ANG SMD | P1 | 56579-0576 | 1
|  | 2 | 27 | CONN POWER JACK 2.1MM | P2 | PJ-002A | 1
|  | 2 | 28 | HEADER 14POS .100" STR TIN, DUAL ROW, 7 x2 | P3 | 67997-472HLF | 0.2
|  | 2 | 29 | CONN RECEPT RTANG 4 POS GOLD PCB | P4 | 5749181-1 | 1
|  | 2 | 30 | CONN JACK STEREO 3POS 3.5MM SMD | P5,P6 | SJ1-3513-SMT | 2
|  | 2 | 31 | CONN EJECT MICROSD PUSH-PUSH SMD | P7 | SCHA5B0200 | 1
|  | 2 | 32 | CONN DB9 FEMALE R/A SOLDER SMD | P8 | 190-009-263R001 | 1
|  | 2 | 33 | EXP_HDR_28 | P9 | LSWSS-114-D-02-T-LF | 1
|  | 2 | 34 | F618-MG -D051-XX-CF358 | P10 | HDR_17x2_1.27mm | 1
|  | 2 | 35 | HDR 10X2_1.27mm | P11,P13,P17 | HDR 10X2_1.27mm | 3
|  | 2 | 36 | HDR 2X2_1.27mm | P18 | HDR 2X2_1.27mm | 1
|  | 2 | 37 | CONN RCPT HDMI R/A SMD | P12 | 10029449-001RLF | 1
|  | 2 | 38 | USB Connectors USB RECEPT ASSEMBLY DOUBLE DECK | P14,P16 | 649-72309-8034BLF | 2
|  | 2 | 39 | CONN MAGJACK 1PRT 10/100B-TX Y/G | P15 | CONN_ETHER_MAG | 1
|  | 2 | 40 | TRANS ARRAY PNP/PNP W/RES S MINI | Q1,Q2 | XP0421400L | 2
BCR135SH6327XT
|  | 2 | 41 | RES ARRAY 10 OHM 5% 8 RES SMD | RP7,RP2,RP3,RP4 | EXB-2HV100JV | 4
|  | 2 | 42 | POLYSWITCH RXE SERIES 0.10A HOLD | RT1 | RXEF010 | 1
|  | 2 | 43 | RES 0.0 OHM 1/10W 5% 0603 SMD | R57,R65,R66,R67,R83,R98,R159 | ERJ-3GEY0R00V | 7
|  | 2 | 44 | RES 10.0K OHM 1/16W 1% 0402 SMD | R1,R8,R24,R25,R31,R37,R38,R41,R42,R43,R54,R62,R72,R73,R74,R75,R76,R77,R81,R86,R90,R93,R94,R103,R106,R107,R108,R118,R123,R124,R125,R128,R129,R130,R135,R138,R140,R141 | RC0402FR-0710KL | 38
|  | 2 | 45 | RES 12.4K OHM 1/10W 1% 0603 SMD | R63 | RC0603FR-0712K4L | 1
|  | 2 | 46 | RES 620K OHM 1/10W 1% 0603 SMD | R9 | MCR03EZPFX6203 | 1
|  | 2 | 47 | RES 12K OHM 1/16W 0.1% 0402 SMD | R48,R49,R109 | RES_12K_.1_0402 | 3
|  | 2 | 48 | RES 200K OHM 1/10W 1% 0603 SMD | R10 | MCR03EZPFX2003 | 1
|  | 2 | 49 | RES 0.10 OHM 1/8W 5% 0805 | R13 | 73L3R10J | 1
|  | 2 | 50 | RES 0.0 OHM 1/3W 5% 1210 SMD | R119 | CRCW12100000Z0EA | 1
|  | 2 | 51 | RES 56.2K OHM 1/16W 1% 0402 SMD | R14,R111 | CRCW040256K2FKED | 2
|  | 2 | 52 | RES 22.6K OHM 1/10W 1% 0402 SMD | R15 | ERJ-2RKF2262X | 1
|  | 2 | 53 | RES 33 OHM 1/16W 5% 0402 SMD | R16,R35,R47,R51,R56,R58,R60,R157 | CRCW040233R0JNED | 8
|  | 2 | 54 | RES 49.9 OHM 1/16W 1% 0805 SMD | R110,R114,R115,R116 | RC0805FR-0749R9L | 4
|  | 2 | 55 | RES 10.0 OHM 1/16W 1% 0402 SMD | R117 | RC0402FR-0710RL | 1
|  | 2 | 56 | RES 1.0K OHM 1/16W 5% 0402 SMD | R17,R88,R91 | CRCW04021K00JNED | 3
|  | 2 | 57 | RES 4.7K OHM 1/16W 5% 0402 SMD | R18,R19,R20,R21,R55,R59,R61,R89,R92,R34 | CRCW04024K70JNED | 10
|  | 2 | 58 | RES 100K OHM 1/16W 5% 0402 SMD | R26,R27,R28,R29,R30,R101,R105 | CRCW0402100KJNED | 7
|  | 2 | 59 | RES 1.65K OHM 1/16W 1% 0402 SMD | R32,R33 | CRCW04021K65FKED | 2
|  | 2 | 60 | RES 330 OHM 1/16W 5% 0402 SMD | R12,R39,R40,R50,R64,R104,R136 | RC0402JR-07330RL | 7
|  | 2 | 61 | RES 32.4K OHM 1/10W 5% 0402 SMD | R113 | CRCW040232K4FKED | 1
|  | 2 | 62 | RES 0.0 OHM 1/16W 5% 0402 SMD | R78,R82,R100,R146,R149,R151,R158 | MCR01MZPJ000 | 7
|  | 2 | 63 | RES 8.45K OHM 1/10W 1% 0603 SMD | R84 | MCR03EZPFX8451 | 1
|  | 2 | 64 | RES 8.06K OHM 1/10W 1% 0603 SMD | R85,R102 | MCR03EZPFX8061 | 2
|  | 2 | 65 | RES, 510 OHM 1/10W 1% 0603 SMD | R87,R121,R23,R137 | RC0402FR-07510RL | 4
|  | 2 | 66 | RES 1M OHM 1/5W 5% 0402 SMD | R112 | RC0402JR-071ML | 1
|  | 2 | 67 | RES 10K OHM 1/16W .1% 0402 SMD | R52,R53,R144 | RES_10K_.1_0402 | 3
|  | 2 | 68 | SWITCH TACT 6MM MOM 100GF | S1,S2 | B3F-1000 | 2
|  | 2 | 69 | IC USB ADJ LDO 5V HP 14-HTSSOP | U2 | TPS2141IPWP | 1
|  | 2 | 70 | Regulators - Low Dropout (LDO) 1.5A LDO Reg | U3,U16 | TL1963ADCQR | 2
|  | 2 | 71 | IC, Processor, DM3730 CBP package ES1.2 | U4 | XDM3730BCBP | 1
|  | 2 | 72 | IC,512MB Memory, POP | U4X | IC_MEM_POP_0G-4G | 1
|  | 2 | 73 | IC BUFF/DVR DL NON-INV SOT236 | U5 | SN74LVC2G07DBV | 1
|  | 2 | 74 | IC DUAL BUFF/DRVR INV W/OD SC70-6 | U18 | SN74LVC2G06DCK | 1
|  | 2 | 75 | IC CTLR OVP 28V W/NMOS 6-DFN | U31,U32 | NCP349MNAE | 2
|  | 2 | 76 | IC PWR MGMT W/11 LDO 209-BGA | U7 | TPS65950BZXN | 1
|  | 2 | 77 | IC LINE DVR/RCVR 1CH 16-TSSOP | U9 | SN65C3221EPWR | 1
|  | 2 | 78 | IC VOLT-LEVEL TRANSLATOR 8-US8 | U10,U12 | TXS0102DCUR | 2
|  | 2 | 79 | IC TRANSMITTER DIGITAL 64-HTQFP | U11 | TFP410PAP | 1
|  | 2 | 80 | IC SWITCH PWR DIST QUAD 16-SOIC | U13 | TPS2054BD | 1
|  | 2 | 81 | IC,USB3326 (CSP) | U14 | USB3320C-EZK | 1
|  | 2 | 82 | IC,Ethernet Controllers USB 4 Port Hub Int 10/100 Ethernet | U15 | LAN9514-JZX | 1
|  | 2 | 83 | 32KHz Crystal | Y3 | FX135A-327 | 1
|  | 2 | 84 | CRYSTAL 25.000 MHZ 20PF SMD | Y4 | ECS-250-20-5PVX | 1
|  | 2 | 85 | ECLIPTEK_26MHZ | Y1 | OSC_26MHZ | 1
Do Not Install: BT1,C9,C209,C141,C142,C200,C201,C202,C203,J1,RP1,RP5,R148,R36,R139,R142,R143,R145,R44,R45,R46,R79,R80,R147,R158,R68,R69,R122,R70,R71,R154,R155,R160,R156,U8,R11,R99,R126,R127,R22
REWORK INSTRUCTIONS
None